## CD
Sl.# | Phase | Task | Subtask | Owner | Planned Start | Planned End | Duration | Status
1 | Infrastructure Setup | Procure a Sanbox for development/testing | Work with FDX IT team | FDX |  |  |  | Completed
|  | Identify tools | Evaluate and identify tools | NOUS |  |  |  | Completed
|  |  | Get TestComplete testing environment | NOUS |  |  |  | Completed
2 | Install and Configure | Install Jenkins and required plugins |  | NOUS |  |  |  | Completed
|  | Install Archiva |  | NOUS |  |  |  | Completed
|  | Install SonarQube |  | NOUS |  |  |  | Completed
|  | Install SonaType |  | NOUS |  |  |  | Completed
|  | Install Contrast |  | NOUS |  |  |  | Completed
3 | Development | Scripts to build source code |  | NOUS |  |  |  | Completed
|  | Security checks | Sonar | NOUS |  |  |  | Completed
|  |  | Jacoco | NOUS |  |  |  | Completed
|  |  | Junit | NOUS |  |  |  | Completed
|  | Full Deployment | Sandbox Deployment | NOUS |  |  |  | Completed
|  | Partial Deployment by removing classpath from Manifest File |  | NOUS |  |  |  | Completed
|  | Test Complete Integration |  | NOUS |  |  |  | Completed
|  | SonaType Integration |  | NOUS |  |  |  | Completed
|  | Upload Artifacts to different repositories(Staging, release etc) |  | NOUS |  |  |  | Completed
|  | Production Deployment | Select build from range of successful artifacts | NOUS |  |  |  | Completed
|  | Deployment Approval |  | NOUS |  |  |  | Completed
|  | Test Interface file validation |  | Nick/Mike |  |  |  | Pending
|  | Patch and Full code - steam options in the pipeline |  | NOUS |  |  | 2019-02-28 | Completed
|  | Monitoring |  | NOUS |  |  |  | Completed
|  | Additing aditional code coverage(Jacoco) |  | DEV |  |  |  | OPEN
|  | Additing test cases for coverage with test complete |  | QA |  |  |  | OPEN
4 | Testing | Manual Testing | Build script | NOUS |  |  |  | Completed
|  |  | Sonar script | NOUS |  |  |  | Completed
|  |  | jacoco script | NOUS |  |  |  | Completed
|  |  | Junit scripts | NOUS |  |  |  | Completed
|  |  | Sandbox Deployment | NOUS |  |  |  | Completed
|  |  | Sonatype integration | NOUS |  |  |  | Completed
|  |  | Validate deployment compatability (dynamic env) | NOUS |  |  |  | Completed
|  |  | Dynamic environment selection for deployment | FDX |  |  | 2019-03-08 | Completed
|  |  | Upload artifacts to different repositories | NOUS |  |  |  | Completed
|  |  | Test interface file validation | Mike (Interface) |  |  |  | Pending
|  |  | Append batch process shell scripts with jar version info | NOuS/FDX |  |  |  | Pending
|  |  | monitoring | NOUS |  |  |  | Completed
|  | UAT(PRODUCTION) | Build script | FDX |  |  |  | Completed
|  |  | Sonar script | FDX |  |  |  | Completed
|  |  | jacoco script | FDX |  |  |  | Completed
|  |  | Junit scripts | FDX |  |  |  | Completed
|  |  | Sandbox Deployment | FDX |  |  |  | Completed
|  |  | Sonatype integration | FDX |  |  |  | Completed
|  |  | Dynamic environment selection for deployment | FDX |  |  | 2019-03-08 | Completed
|  |  | Upload artifacts to different repositories | FDX |  |  | 2019-03-08 | Completed
|  |  | Test interface file validation | FDX |  |  |  | Pending
|  |  | Full and partial code streaming options | FDX |  |  | 2019-03-08 | Completed
|  |  | monitoring | FDX |  |  |  | Not Required for now
5 | Migration | Production Implementation | Single Profile Deployment | FDX |  |  | 2019-03-13 | Completed
|  |  | Multi Profile Deployment | FDX |  |  | 2019-03-15 | In-Progress
Q1 2019 deadline for production

## Interface BuidDeployment
Sl.# | Phase | Task | Subtask | Owner | Planned Start | Planned End | Duration(in Days)
1 | Infrastructure Setup | Procure Setup | Work with FDX IT team | FDX
|  | Identify tools | Evaluate and identify tools(e.g. FlywayDB or any opensource tools) | NOUS |  |  | 5
2 | Install and Configure | Install and configure the tool identified |  | NOUS |  |  | 2
3 | Requirement Definition | Analyze exisitng workflow |  | NOUS/FDX |  |  | 2
|  | Review the artificts |  | NOUS/FDX
|  | Understanding current setup |  | NOUS/FDX
|  | Review the process changes for CICD |  | NOUS/FDX/Mike
|  | Finalize the requirements |  | NOUS/FDX/Mike
3
4 | Analysis | Further analysis on requirements
5 | Development | Implemet the needed chnages |  | NOUS |  |  | 15
|  | Based on the Tools Analyzed(or own scripts) develop deployment model |  | NOUS |  |  | 15
6 | Testing | Batch/interface testing/validations |  | FDX/Mike |  |  | 10
|  | Fix issues |  | NOUS |  |  | 5
7 | Approval | Get Approval for deploying to production |  | NOUS/FDX
Note : | Line 12 - If we need to create own scripts/tool, the timeline might change
|  |  |  | Total | 60 days | days
Questions
1. Are we changing the flow and why?

## Database Migration
Sl.# | Phase | Task | Subtask | Owner | Planned Start | Planned End | Duration(in Days)
1 | Infrastructure Setup | Procure a VM to install database | Work with FDX IT team | FDX
|  | Identify tools | Evaluate and identify tools(e.g. FlywayDB or any opensource tools) | NOUS |  |  | 5
|  |  | Work with FDX Finance team | NOUS
2 | Install and Configure | Install and configure the tool identified |  | NOUS |  |  | 2
3 | Requirement Definition | Understanding DB2 |  | NOUS/FDX |  |  | 2
|  | Understanding current Database deployment strategy |  | NOUS/FDX |  |  | 3
4 | Analysis | Analyze FlywayDB or any other opensource tools or create a new tool |  | NOUS |  |  | 2
|  | Prepare DB(DDL/DML) Versioning Strategy |  | NOUS |  |  | 5
|  | Prepare documentation and get approval |  | NOUS |  |  | 2
5 | Development | Migrate existing DB Schemas(DDL/DML) into new versioning strategy |  | NOUS |  |  | 15
|  | Based on the Tools Analyzed(or own scripts) develop deployment model |  | NOUS |  |  | 15
|  | Transition to DB team |  | FDX |  |  | 15
6 | Testing | Test the DB deployment model in local sandbox |  | NOUS |  |  | 5
|  | Test in DB deployment model in QA/QUAT |  | FDX
|  | Fix issues |  | NOUS |  |  | 5
7 | Approval | Get Approval for deploying to production |  | NOUS/FDX
Note : | Line 12 - If we need to create own scripts/tool, the timeline might change
|  |  |  | Total | 76 | days

## Microservice
Sl.# | Phase | Task | Subtask | Owner | Planned Start | Planned End | Duration
1 | Requirement Definition | Microservice Tools and Features | Microservice Tools and Features | NOUS/FDX |  |  | 3
|  | Scaling Requirements | Scaling Requirements | NOUS/FDX |  |  | 3
|  | Load Balancing Requirements | Load Balancing Requirements | NOUS/FDX |  |  | 3
2 | Infrastructure Requirement | Sandbox VM |  | FDX
3 | Development | Application(Chef/Ansible) | Java | NOUS |  |  | 2
|  |  | Springboot | NOUS |  |  | 2
|  |  | Other Tools/Softwares |  |  |  | 5
|  |  | Firewall Configurations | NOUS |  |  | 5
|  |  | System settings configurations | NOUS |  |  | 5
|  |  | Chef Environments | NOUS |  |  | 5
|  |  | Chef Roles | NOUS |  |  | 5
|  |  | Health Monitoring | NOUS |  |  | 5
|  |  | Database | NOUS |  |  | 5
|  |  | SSL Certificate Configuration | NOUS |  |  | 5
|  |  | 3rd Party Application installation checks | NOUS |  |  | 5
|  | Application (Containerization) | Dockerize Application Deployment | NOUS |  |  | 10
|  |  | Orchestrate Application Deployment using Kubernates | NOUS |  |  | 20
4 | Testing | Automated Application Testing (Chef-Inspec) | Application Checks | NOUS |  |  | 5
|  |  | System Checks | NOUS |  |  | 5
|  | Manual testing | Springboot | NOUS |  |  | 1
|  |  | Other Tools/Softwares | NOUS |  |  | 1
|  |  | Firewall Configurations | NOUS |  |  | 1
|  |  | System settings configurations | NOUS |  |  | 1
|  |  | Chef Environments | NOUS |  |  | 5
|  |  | Chef Roles | NOUS |  |  | 5
|  |  | Health Monitoring | NOUS |  |  | 2
|  |  | Database | NOUS |  |  | 5
|  |  | SSL Certificate Configuration | NOUS |  |  | 1
|  |  | Java | NOUS |  |  | 1
|  | UAT | Springboot | FDX
|  |  | Other Tools/Softwares | FDX
|  |  | Firewall Configurations | FDX
|  |  | System settings configurations | FDX
|  |  | Chef Environments | FDX
|  |  | Chef Roles | FDX
|  |  | Health Monitoring | FDX
|  |  | Database | FDX
|  |  | SSL Certificate Configuration | FDX
FDX
5 | Approval | Approval |  | FDX
[5 empty] | Total | 121 | days
Note: Some of the items are already taken care in Openstack Integaration.
Also depends on the Microservice development architecture(Items like service discovery, caching, auto load balancing etc is taken care by development team). If not, need to re-visit the estimates
GIT Labs training and transistion is not estimated

## Openstack Integration(Manual)
Sl.# | Phase | Task | Subtask | Owner | Planned Start | Planned End | Duration(in days)
1 | Requiremnt Definition | Understand the requirements w.r.t Openstack Manual Provisioning | Openstack Infrastructure | NOUS/FDX |  |  | 5
|  |  | Storage Requirement | NOUS/FDX |  |  | 2
|  |  | Network Requirement(VLAN) | NOUS/FDX |  |  | 2
|  |  | Disaster Recovery | NOUS/FDX |  |  | 3
|  |  | Replication Requirement | NOUS/FDX |  |  | 3
|  |  | Availability Zones Requirement | NOUS/FDX |  |  | 3
|  |  | Image Management(Glance) | NOUS/FDX |  |  | 2
|  |  | Identity Service Management(Keystone) | NOUS/FDX |  |  | 2
|  |  | Orchestration (Heat) | NOUS/FDX |  |  | 5
|  |  | Openstack Upgrade Plans | NOUS/FDX |  |  | 5
|  | Understand the requirements w.r.t Application | Database/Application Servers/Other Applications | NOUS/FDX |  |  | 1
|  |  | Application Load Balancing | NOUS/FDX |  |  | 1
|  |  | High Availability(N+M Redundancy) | NOUS/FDX |  |  | 1
|  |  | Backup and Restore | NOUS/FDX |  |  | 2
|  |  | Health Monitoring(Neutron, Cinder, Node) | NOUS/FDX |  |  | 1
|  |  | Storage Requirement(Connecting Cinder block to multiple nodes) | NOUS/FDX |  |  | 2
|  |  | Application recovery when Storage(Cinder) Crash/Node Crash | NOUS/FDX |  |  | 2
2 | Infrastructure Setup | Access to Openstack Infrastructure | FDX to provide access to Nous devops team for accessing infrastructure | FDX
|  |  | Understand and analyze the infrastructure | NOUS |  |  | 10
|  |  | Manually provision the infrastructure using Horizon/any other management tool | NOUS |  |  | 5
3 | Development | Software Installtion(Chef) | Setup Base Chef infrastructure with Kitchen Environment | NOUS |  |  | 15
|  |  | Java installation | NOUS |  |  | 2
|  |  | Websphere/Any other Application server Installation | NOUS |  |  | 5
|  |  | Install other depended softwares | NOUS |  |  | 6 | (depends on how many depended softwares need to be installed - 2 days/software)
|  |  | Database Installation | NOUS |  |  | 10
|  |  | Health Monitoring | NOUS |  |  | 5
|  | Application(Chef) | Install application | NOUS |  |  | 3
|  |  | Springboot application(Microservice) | NOUS |  |  | 2
|  |  | Chef Environment(Dev, QA, QUAT, Prod1, Prod2 etc) | NOUS |  |  | 10
|  |  | Chef Roles for instances | NOUS |  |  | 10
|  |  | Run DB Scripts | NOUS |  |  | 10
|  |  | Health Monitoring | NOUS |  |  | 5
|  | System Configuration(Chef) | Firewall Settings | NOUS |  |  | 10
|  |  | Health Monitoring | NOUS |  |  | 5
|  |  | System wide settings(uLimits, Logs etc) | NOUS |  |  | 5
|  | Openstack(Shell script/Chef/Heat) | Cinder Attach/Detach scripts in case of node crash | NOUS |  |  | 15
|  |  | Add/Remove nodes from Load Balancer | NOUS |  |  | 15
|  |  | Replicated cinder attach (in case of Cinder crash) | NOUS |  |  | 10
|  |  | High Availability(N+M Redundancy) | NOUS |  |  | 10
|  |  | Disaster Recovery Configuration(Network and Nodes) | NOUS |  |  | 10
|  |  | Image Management(Glance) | NOUS |  |  | 10
|  |  | Node Orchestration(Heat) | NOUS |  |  | 20
|  |  | Identity Service Management(Keystone) | NOUS |  |  | 10
|  | Health Monitoring scripts | Softwares(line 22-26) | NOUS |  |  | 5
|  |  | System(line31-33) | NOUS |  |  | 5
|  |  | Application(line 27-30) | NOUS |  |  | 5
|  |  | Openstack(line34-41) | NOUS |  |  | 5
4 | Testing | Automated Testing(Inspec) | Base Inspec setup | NOUS |  |  | 5
|  |  | Softwares(line 22-26) | NOUS |  |  | 5
|  |  | System(line31-33) | NOUS |  |  | 5
|  |  | Application(line 27-30) | NOUS |  |  | 5
|  | Manual Testing | Softwares(line 22-26) | NOUS |  |  | 10
|  |  | System(line31-33) | NOUS |  |  | 10
|  |  | Application(line 27-30) | NOUS |  |  | 10
|  |  | Openstack(line34-41) | NOUS |  |  | 10
|  | Stress/Perfomance/Load Testing | Softwares(line 22-26) | NOUS
|  |  | System(line31-33) | NOUS
|  |  | Application(line 27-30) | NOUS
|  |  | Openstack(line34-41) | NOUS
|  | UAT | Softwares(line 22-26) | FDX
|  |  | System(line31-33) | FDX
|  |  | Application(line 27-30) | FDX
|  |  | Openstack(line34-41) | FDX
5 | Approval | Approval |  | FDX
NOTE : | Stages are considering Openstack environment would be managed by a different vendor(RedHat or someone)
Some of the stages may be removed/added depending on the Openstack cloud provider, Features required etc
If Nous need to provide support for creating Openstack environment, Need to revisit on the stages
[5 empty] | Total | 340 | days

## Openstack Ingeration(Automatic)
Sl.# | Phase | Task | Subtask | Owner | Planned Start | Planned End | Duration(in days)
1 | Requirement Definition | Understand the requirements w.r.t Openstack Auto Provisioning |  | NOUS/FDX |  |  | 5
|  | Understand the requirements w.r.t Openstack Auto Provisioning |  |  |  |  | 5
2 | Infrastructure Setup | Access to Openstack Infrastructure | FDX to provide access to Nous devops team for accessing infrastructure | FDX
|  |  | Understand and analyze the infrastructure | NOUS |  |  | 5
|  |  | Manually provision the infrastructure using Horizon/any other management tool | NOUS |  |  | 15
3 | Development | Cluster Management(Terraform Script/Shell Scripts/Chef Cookbooks/Heat) | Create Node and adding to cluster | NOUS |  |  | 10
|  |  | Cinder Management | NOUS |  |  | 5
|  |  | Multi node attach cinder | NOUS |  |  | 5
|  |  | VLAN Management(Neutron) | NOUS |  |  | 10
|  |  | Identity Management(Keystone) | NOUS |  |  | 5
|  |  | Replication Management | NOUS |  |  | 5
|  |  | Availability Zones Management | NOUS |  |  | 5
|  |  | Image Management(Glance) | NOUS |  |  | 10
|  |  | Identity Service Management(Keystone) | NOUS |  |  | 10
|  |  | Orchestration (Heat) | NOUS |  |  | 10
|  |  | Health Monitoring and Management | NOUS |  |  | 10
| Testing | Cluster Management(Automatic) | Create Node and adding to cluster | NOUS |  |  | 10
|  |  | Cinder Management | NOUS |  |  | 10
|  |  | Multi node attach cinder | NOUS |  |  | 5
|  |  | VLAN Management(Neutron) | NOUS |  |  | 10
|  |  | Identity Management(Keystone) | NOUS |  |  | 5
|  |  | Replication Management | NOUS |  |  | 5
|  |  | Availability Zones Management | NOUS |  |  | 5
|  |  | Image Management(Glance) | NOUS |  |  | 5
|  |  | Identity Service Management(Keystone) | NOUS |  |  | 5
|  |  | Orchestration (Heat) | NOUS |  |  | 15
|  |  | Health Monitoring and Management | NOUS |  |  | 5
|  | Stress/Performance/Load Testing | Application | NOUS |  |  | 20
|  |  | System | NOUS |  |  | 20
|  |  | Openstack | NOUS |  |  | 20
|  | UAT | Create Node and adding to cluster | FDX
|  |  | Cinder Management | FDX
|  |  | Multi node attach cinder | FDX
|  |  | VLAN Management(Neutron) | FDX
|  |  | Identity Management(Keystone) | FDX
|  |  | Replication Management | FDX
|  |  | Availability Zones Management | FDX
|  |  | Image Management(Glance) | FDX
|  |  | Identity Service Management(Keystone) | FDX
|  |  | Orchestration (Heat) | FDX
|  |  | Health Monitoring and Management | FDX
5 | Approval | Approval |  | FDX
|  |  |  | Total | 255 | days